## Project Plan Dashboard
Activities Dashboard
Overall Project Activities Status | Title: | Activities and Projects
Completed | Report Date | Week of March 29th 2021
Sandy T | Overall Status | On Track
French Network and Speciality Agreements to One Agreement
Sandy/Morgen | Project Activities | Assigned To | Priority | Status | Percentage % Complete
Process Reviews (Meng's Meetings) | ATI Documentation for Business | Mayur/Marco/Sandy | ★ | In Progress | 25%
In Progress | ATI UAT Delivery - Traffic | Mayur and Marco | ★ | In Progress | 10%
Evan T | ATI UAT Delivery - Sales | Sandy T | ★ | In Progress | 10%
Oracle Upgrade Test Plan | French Network and Speciality Agreements to One Agreement | Sandy T |  | Completed | 100%
Oracle Upgrade Testing Tracking | Oracle Upgrade Test Plan | Evan T | ★ | In Progress | 10%
Mayur and Marco | Oracle Upgrade Testing Tracking | Evan T | ★ | In Progress | 10%
ATI UAT Delivery - Traffic | Oracle Upgrade Testing | Sandy T | ★ | In Progress | 5%
Mayur K | Reversal CR-1345 Defects/Process review | Victor L | ★ | In Progress | 75%
RPA - Traffic Discussions/Enhancements | Non-Airtime LambEDI | Victor L |  | In Progress | 10%
Mayur/Marco/Sandy | Dev Express Invoice Testing/Process review | Victor L | ★ | In Progress | 75%
ATI Documentation for Business | Process Reviews (Meng's Meetings) | Sandy/Morgen |  | Completed | 100%
Sandy T | RPA - Traffic Discussions/Enhancements | Mayur K | ★ | In Progress | 60%
ATI UAT Delivery - Sales | New Sales Group - National Sales Toronto | Sandy T |  | On Hold | 5%
Oracle Upgrade Testing
Victor L
Dev Express Invoice Testing/Process review
Non-Airtime LambEDI | Day to Day Activities/Tasks | Assigned To
Reversal CR-1345 Defects/Process review | Scorecard Testing Tracking | Sandy T/Chiove
On Hold | SAM Day to Day Activities | Marina/Jack/Marco
Sandy T | Patch Upgrades/Maintainence | Marina
New Sales Group - National Sales Toronto | Confluence Page Maintainence | Evan T
Grand Total | Admin Tasks - IBMS and Wide Orbit | Jack N

## Tasks Assignments
Projects Tasks/Activities
Tasks | Assigned To | Resource Allocation | Start | End | Current Days | Target Date of Completion | Action Items | Decisions/Notes | Percentage % Complete | Status
ATI Documentation for Business | Mayur/Marco/Sandy | 33.3% | 2021-03-15 | 2021-04-16 | 32 | 2021-04-16 | Process guide including Visio - for Traffic Cheat sheet IBMS (same /new) Training EUD for Cloverleaf Sales Form Lorenzo -Quick Reference Guide (hyperlinks) with Business scenarios/usage Agenda for training Web from (to be used to train Patty) Agenda for training Web from (to be used to train Traffic) CR communication - Cloverleaf EN CR communication - IBMS EN CR communication - Cloverleaf - Translate to French CR communication - IBMS - Translate to French |  | 25% | In Progress
ATI UAT Delivery - Traffic | Mayur and Marco | 50% | 2021-03-15 | 2021-04-16 | 32 | 2021-04-16 | UAT in April 2021 Meeting Invite to be sent to SME |  | 10% | In Progress
ATI UAT Delivery - Sales | Sandy T | 100% | 2021-03-15 | 2021-04-16 | 32 | 2021-04-16 | UAT in April 2021 Meeting Invite to be sent to SME |  | 10% | In Progress
French Network and Speciality Agreements to One Agreement | Sandy T | 100% | 2021-03-15 | 2021-03-29 | 14 | 2021-03-29 | Process to maintain one French Agreement than Multiple Agreements | 03.29 - Email sent to Sophie Menard Process Document emailed | 100% | Completed
Oracle Upgrade Test Plan | Evan T | 100% | 2021-03-15 | 2021-04-23 | 39 | 2021-04-23 | Solution Test cases - Organizing the Folders Test Cases Review with Progamming SME's Meetings Set up On Demand Test Cases to be written |  | 10% | In Progress
Oracle Upgrade Testing Tracking | Evan T | 100% | 2021-03-15 | 2021-04-23 | 39 | 2021-04-23 | Tracking of the Solution Test cases |  | 10% | In Progress
Oracle Upgrade Testing | Sandy T | 100% | 2021-03-15 | 2021-04-23 | 39 | 2021-04-23 | Meeting with SME to review Solution Test cases |  | 5% | In Progress
Reversal CR-1345 Defects/Process review | Victor L | 100% | 2021-01-01 | 2021-05-16 | 135 | 2021-05-16 |  |  | 75% | In Progress
Non-Airtime LambEDI | Victor L | 100% | 2021-01-01 | 2021-05-16 | 135 | 2021-05-16 |  |  | 10% | In Progress
Dev Express Invoice Testing/Process review | Victor L | 100% | 2021-01-01 | 2021-05-16 | 135 | 2021-05-16 |  |  | 75% | In Progress
Process Reviews (Meng's Meetings) | Sandy/Morgen | 50% | 2021-02-25 | 2021-06-25 | 120 | 2021-05-16 | TX Profile - Allocation View for Rev Man PC Dashboard Presentation Slides | 03.29 - Completed Email Sent to Rev Man 03.29 - Presentation sent to Morgen | 100% | Completed
RPA - Traffic Discussions/Enhancements | Mayur K | 100% | 2021-02-25 | 2021-06-25 | 120 | 2021-05-16 |  |  | 60% | In Progress
New Sales Group - National Sales Toronto | Sandy T | 100% | [6 empty] | 5% | On Hold
Day to Day Activities/Tasks
Tasks | Assigned To | Resource Allocation | Action Items | Decisions/Meeting Notes | Next Steps | Date
Scorecard Testing Tracking | Sandy T/Chiove | 50% | Opening IBMS - Performance Slowness | Next steps - ST to Work with Chiove to identify trend and work with Citrix and DBA Team | Meeting with Chiove | 03.29.2021
SAM Day to Day Activities | Marina/Jack/Marco | 33.3% | Smart Sheet Updates |  |  | 03.29.2021
Server and Patch Upgrades/Maintainence | Marina | 100% |  |  |  | 03.29.2021
Confluence Page Maintainence | Evan T | 100% |  |  |  | 03.29.2021
Admin Tasks - IBMS and Wide Orbit | Jack N | 100% |  |  |  | 03.29.2021